Specific Statement of Work for the Thermal Hardware (THW) for the S2NG mission

| DRL-No.: N/A | This text is for additional project specific information as required, e.g. CI-No. or DRL-No. Enter specific IDs here. If not needed, insert NA. |
| --- | --- |
| CI-No.: TBC |  |

| Prepared by: |  |  | Date : |  |
| --- | --- | --- | --- | --- |
|  | Name / Function: | Christopher Speidel / Thermal Architect |  |  |
| Approved by: |  |  | Date : |  |
|  | Name / Function: | Sabine Pröll / Industrial Management |  |  |
| Approved by: |  |  | Date : |  |
|  | Name / Function: | Martijn Theunissen / Chief Engineer |  |  |
| Released by: |  |  | Date : |  |
|  | Name / Function: | Marcus Glatt / Project Manager |  |  |

Approval and release information:

This document has been approved either by manual signatures as shown above, or via electronic workflow as shown on the cover page preceding this page.

Security information:

Security information applies either  by manual signatures in the box below or by electronic workflow as shown in the box on the cover page preceding this page.

Export Control Information concerning this document’s content

Section 1 (not applicable in France, please go to section 3)

This document contains Technical Information:

Yes      No

If No to section 1: Please complete section 2

If Yes to section 1: Please complete section 3 as applicable

Section 2 (not applicable in France, please go to section 3)

I confirm the document does not contain Technical Information and is “Not-Technical”.

Name:	Sabine Pröll

Date:	04.03.2026

Section 3

3a. National and EU regulations Export Control Assessment

This document has been assessed against applicable export control regulations in

France       Germany       Spain       UK       Other: [specify country]

and does not contain Controlled Technology1 and is therefore “Not Listed / Not Controlled”.

and contains Controlled Technology with export control classification [insert classification number, e.g. ML22x, xExxx, AMAx].

Note:	Any transfer of this document in part or in whole must be made in accordance with the appropriate export control regulations. Prior to any transfer outside of the responsible legal entity, confirmation of an applicable export licence or authorisation must be obtained from the local Export Control Officer (ECO).

3b. US (ITAR / EAR) Export Control Assessment

This document does not contain US origin Technical Data (Technology)

This document contains “Technology” which is controlled by the U.S. government under [USML category number / ECCN] and which has been received by [legal entity] under the authority of [licence number / ITAR exemption / EAR licence exception / NLR].

This document contains technology which is designated as EAR99 (subject to EAR and not listed on the USML/CCL).

Note:	Any re-export or re-transfer of this document in part or in whole must be made in accordance with the appropriate regulation (ITAR or EAR) and applicable authorization. If in any doubt please contact your local ECO.

3c. Technical Rater Information

This document has been assessed by the following Technical Rater:

Assessed and classified by:

Date classification completed:

“Controlled Technology” is defined as any Information necessary for the design, development, production, use, operation, maintenance or repair of export controlled goods. Examples of such Information are blueprints, plans, diagrams, models, engineering designs, manuals, requirements specifications and instructions etc. If in any doubt please contact your local Export Control Officer (ECO).

DOCUMENT CHANGE DETAILS

| Version | Date | Modified Pages | Description of Change |
| --- | --- | --- | --- |
| 1 | 04/03/2026 | All | 1st Issue |

DISTRIBUTION

| Quantity | Date | Name | Organisation |
| --- | --- | --- | --- |
| 1 | See issue date | S2NG Team |  |

CONTENTS

1	Introduction	5

1.1	Background	5

1.2	Document Scope and Objectives	5

2	Applicable and Reference Documentation	6

2.1	Applicable Documents	6

2.2	Normative Documents	7

3	Specific Design, Engineering, Analyses and Verification Tasks	7

3.1	Task overview	7

3.2	Objectives of phase C/D	7

3.3	Engineering and Design	8

4	Deliveries S2NG	10

4.1	Hardware Deliveries	10

4.2	Thermal Hardware Integration Activities	10

4.3	Software and Firmware deliveries	10

4.4	Data and Mathematical Models	10

4.5	Ground Support Equipment Deliveries	11

4.6	Spares	11

4.7	Options	12

4.8	Customer Undertakings	12

4.9	Delivery Address	12

5	Milestones, Meetings and Review Dates	13

6	Specific Requirements and Post Delivery Requirements	14

6.1	Integration	14

6.2	Specific Support and Post Delivery Requirements Mission S2NG.	14

6.3	Specific Support to Phase E1	14

6.4	Lifetime, Long Storage and Maintenance	14

6.5	Life Cycle Assessment (LCA)	14

7	Documentation	15

7.1	Documentation for unit falling in Category C or D	16

TABLES

Table 2-1: Applicable Document List	6

Table 4-1: S2NG Hardware Delivery Requirements	10

Table 4-2: Definition of H/W Spare Items	11

Table 4-3: Customer Undertakings	12

Table 5-1: S2NG Meetings and Review Dates	13

# Introduction

## Background

In the frame of the Copernicus Program, coordinated and managed by the European Commission, the European Space Agency, under the mandate to define the overall system architecture for the Copernicus Space Component, has defined the Sentinel-2 Next Generation (Sentinel-2NG) mission to provide enhanced continuity to the Sentinel-2 services provided by the first generation.

## Document Scope and Objectives

This Contractor’s Specific Statement of Work (SSOW) defines work to be performed by the Contractor under the contractual authority of the S2NG Customer Contractor, Airbus Defence and Space GmbH.

The “European Space Agency” (hereinafter referred to as “ESA” or “the Agency”) is the S2NG Mission end-customer.

Airbus Defence and Space GmbH is the Prime Contractor (hereinafter referred to as the “ Prime”) for the Implementation Phase of the S2NG spacecraft.

The “Contractor” is the supplier of all the work as defined in this Contractor’s SSOW.

The use of “shall”, “should”, “must”, “will”, “may” and “could”:

- The word “shall” in the text denotes a mandatory requirement. Deviation from such a requirement is not permissible without the formal agreement of Airbus Defence and Space.

- The word “should” in the text denotes a recommendation or advice on implementing a requirement. Such recommendation or advice is expected to be followed unless good reasons are stated for not doing so.

- The words “must” or “will” in the text denotes a provision, a service or an intention in connection with a requirement.

- The words “may” or “could” in the text denote a permissible practice or action and do not express a requirement.

This Specific statement of Work (SSOW) is applicable in conjunction with the Generic SOW (GSOW), which defines the equipment generic requirements. In case of conflict, this specific statement of work shall have precedence.

The structure of this Equipment Specific Statement of Work follows the general outline of the standardized SSoW established for S2NG, adapted to the specifics of the Equipment development.

# Applicable and Reference Documentation

## Applicable Documents

The work carried out by the Contractor and the Contractor’s lower-level Subcontractors shall be performed in accordance with the following applicable documents which form an integral part of the Contractor’s SOW. Unless a specific issue of a document is mentioned, the current issue shall apply. When a specific issue is referenced, only that issue applies.

In case technological limitations lead to non-compliances these non-compliances shall be justified and identified as risks by the Contractor for assessment on system level by the Customer. To support this assessment the Contractor shall define the best achievable value/ solution.

This document aims to provide an exhaustive list of applicable documents for the S2NG. The applicable issues of these documents are specified here below. The referenced AD documents have been separated in 3 sections:

- (D) Detailed SoC: Project documents listed for which a detailed compliance matrix is required.

- (G) General Statement: Project documents listed for which a detailed compliance matrix is not required, but a general statement of compliance is sufficient. Although no detailed compliance matrix is required, major non-compliances, if any, shall be reported/highlighted.

- (AM) applicability matrix: SoC for each requirement, which is applicable through the corresponding Applicability Matrix.

- Normative documents:, that are well known from European space industry and widely applicable for all ESA projects. This includes mainly the ECSS standards. Although no detailed compliance matrix is requested wrt all these standards, major non compliances, if any, shall be reported/highlighted.

According to these pre-defined sections, the applicability matrix of is the following:

| AD # | Title | Reference | Issue | SoC |
| --- | --- | --- | --- | --- |
| AD00 | Multi-Layer Insulation (MLI) Contractual Applicable Document List (CADL) | SPS_MSC-LI-1000181994 | 3 | D |
| AD01 | Specific Statement of Work for Thermal Hardware | this document |  | D |
| AD03 | Thermal Hardware Specification | S2NG-SP-ADSF-SYS-1002224374 | 1 | D |
| AD08 | S3NGT Product Assurance Requirements for Suppliers* | S3NGT-SP-ADSF-1000262 | 1 | D |
| AD13 | Thermal Hardware Input CAD model | S2NG-210000A00C (STP File) | n.a. | G |
| AD47 | Generic Space Environment for EOS Polar Orbits Missions | SPS-ADSF-SP-1001783153 | 1 | D |

Table 2-1: Applicable Document List

*Note 1:

The PA Requirements for subcontractor (AD08) supersede the Generic ENS Class-1 PA requirements (AD09) for suppliers as defined in the CADL (AD00).

## Normative Documents

The ECSS standard is applicable in its entirety in version C, latest revision available at the issue date of the RfP. Tailoring of the ECSS by the applicable documents listed in section 2.1 supersedes the corresponding elements of the ECSS.

# Specific Design, Engineering, Analyses and Verification Tasks

## Task overview

The Subcontractor shall be responsible for the provision of all materials, manpower, facilities, supplies, tools, equipment, documentation and support services as may be required to design, manufacture, assemble, test and deliver to Airbus DS the end products and services as specified in this SOW and the Generic SOW (as per CADL), according to the Applicable Documents in Section 2.

The requirements of this SSOW shall also be made applicable to the contractually specified Lower Level Subcontractors/Suppliers, as pertinent to their work shares. Therefore the word "Supplier" shall be interpreted as “Supplier and Lower Level Subcontractors/Suppliers”, if not specifically restricted by appropriate formulations. Hardware and Software from other sources, such as Off the Shelf (OTS) items, shall be procured according to the equivalent technical, quality and safety related requirements.

## Objectives of phase C/D

The objectives of the Phase C/D of the passive thermal hardware program to be met by the Supplier/Contractor are:

- Development of the MLI design

- Manufacture of the hardware items requested by the Deliverable Items List in this SOW,

- Acceptance testing of qualified equipment models (samples),

- Delivery to Airbus DS GmbH, integration and support during satellite AIV and test.

- Procurement of FSSM foil/tape

The main tasks to be performed in order to achieve the above objectives are:

- establishment of all detailed plans and requirements for the design, development, integration and qualification of the equipment,

- establishment of the equipment parts list,

- finalisation of the critical items- and of the long lead items list,

- preparation of the MLI templates as data file and printout on cleanroom paper and integration drawings,

- conduct the equipment verification program (e.g. including testing and analyses),

- carry out the required PA activities,

- preparation of supporting plans, analyses etc. as called for in this SOW,

- manufacture of the items requested in the DIL and the necessary support equipment,

- conduct the equipment level reviews,

- MLI & FSSM integration on satellite.

## Engineering and Design

The Passive Thermal Hardware consists of different MLI blankets and Flexible Second Surface Mirror (FSSM) covered areas detailed in the Thermal Hardware requirement specification:

- External MLI blankets covering the spacecraft structure panels

- External MLI blankets covering the propulsion module including thruster assembly

- External MLI blankets covering brackets, antennas and to close mechanical or electrical interface access holes

- External MLI blankets covering the battery modules

- Internal MLI blankets covering the tank cone, propellant and pressurant tanks

- Internal MLI blankets covering the platform top floor at the interface to the instrument

- Flexible Second Surface Mirror for radiator areas

Key design features as specified in AD03:

- The Passive Thermal Hardware shall enable a passive thermal control of the spacecraft by providing a minimum specified thermal performance. This incorporates

  - the expected temperature domain

  - the heat transfer coefficient (MLI)

  - thermo-optical surface properties

- For AIT operations MLI shall be designed to be dismountable/mountable several times

  - Frequently removed/stressed blankets shall have a dedicated set of test MLI (detailed in AD03)

There will be three sets of Thermal Hardware:

- One set for SAT-A

- One optional set for SAT-B

- One optional set for SAT-C

The thermal hardware supplier responsibility shall include:

- Establish a suitable equipment design (MLI layout, blanket sizing as well as fixation and grounding on the structure), development and verification philosophy and check the compliance with the Thermal Hardware requirements. The thermal hardware items described in the requirements specification are all TBC and can vary in details until equipment (MLI) CDR.

- Define and procure all necessary supports, brackets, assembly kits, fasteners and grounding wires to assemble and integrate the MLI and FSSM radiator surfaces to the structure/equipment. Additional structures, which are needed to fix the MLI shall be negotiated with the customer.

- Select appropriate parts, materials and processes and identify Long Lead Items

- Support S/C level MGSE interface, stay-out zones and attachment points definition

- Prepare MLI templates as data file and printout on cleanroom paper and integration drawings

- Establish detailed configuration drawings / CATIA model

- Monitor and control Thermal hardware budgets (mass and detailed mass properties)

# Deliveries S2NG

The following sections provide a list of the items to be delivered together with the date and place of delivery.

## Hardware Deliveries

Physical arrival of the equipment at customer premises shall take place not later than 1 week after DRB.

Note: The Dates of the milestones are in defined in chapter 5.

| Hardware Items | Quantity | Delivery Date |
| --- | --- | --- |
| THW 1st Flight Set (SAT-A) | 1 | 1st Flight Set DRB |
| THW Test Set (MLI) | 1 | Test Set DRB |
| Optional THW 2nd Flight Set (SAT-B) | 1 | 2nd Flight Set DRB |
| Optional THW 3rd Flight Set (SAT-C) | 1 | 3rd Flight Set DRB |
| Spare approach as defined in 4.6 | 1 | 3 months after 1st flight set |

Table 4-1: S2NG Hardware Delivery Requirements

For each delivery: Delivered in suitable Transport Container and any cables, harness jigs and tools needed for handling of the unit.

The Hardware shall be delivered in a visibly clean state, verified by inspection under white light at the suppliers premises as per ECSS-Q-ST-70-01. The maximum levels of allowable contamination being MOC (200ng/cm2) and PAC (300ppm).

## Thermal Hardware Integration Activities

The Option to integrate the Thermal Hardware is a Mandatory Option.

Generally the thermal hardware shall be delivered to Airbus Defence and Space GmbH and integrated to the satellite in Airbus Defence and Space GmbH’s clean room.

## Software and Firmware deliveries

No separate software and firmware deliveries are expected.

## Data and Mathematical Models

[GSOW §7.1.3]: The following items are required to be delivered in addition.

| No. | Item | Version / Release | Delivery Date | Place of Delivery |
| --- | --- | --- | --- | --- |
| 1 | CAD model in CATIA compatible format (eg STEP AP214) | V1 | At Kick-Off | Airbus Defence & Space GmbH, Immenstaad |
| 2 | MLI thermal performance data * |  | With DRB | Airbus Defence & Space GmbH, Immenstaad |
| 3 | All blanket and bonding templates shall be provided in a 1:1 scale vector format readable by the customer. Preferred formats are: pdf, hpgl, dxf, cgm |  | With DRB | Airbus Defence & Space GmbH, Immenstaad |

(*) for MLI and radiator FSSM, thermal performance (effective emissivity, heat transfer coefficient, thermo-optical surface properties) temperature-dependant performance data shall be provided.

## Ground Support Equipment Deliveries

Ground Support Equipment (GSE) necessary to transport, protect, store, handle and integrate the unit within the spacecraft shall be delivered. In particular, the Supplier shall deliver the hardware items in appropriate reusable containers.

The contractor shall provide an itemized price breakdown for all GSE.

GSE shall be delivered in accordance with Generic Statement of work.

## Spares

A spare approach shall be prepared, demonstrating an acceptable level of risk, to be agreed with Airbus Defence and Space.

Spare items shall be properly stored as flight hardware until their date of delivery. Operational and storage

constraints shall be provided by the contractor to allow the adequate storage of the spare items from their date of delivery until the launch of S2NG.

In case of repair of a damaged equipment, the supplier shall make all efforts to minimise the schedule impacts. During the launch campaign, full priority of manpower, GSE, and other resources necessary shall be allocated.

The supplier has to ensure that all requirements as defined in the GSOW are fulfilled to allow the repair of

flight standard.

Note: The supplier shall take in consideration the On Ground Life and shelf life requirements as input to the

spare scenario.

Table 4-2: Definition of H/W Spare Items

| H/W Spare Items | Quantity | Delivery Date |
| --- | --- | --- |
| Flight MLI | To be defined by Subcontractor | 3 months after 1st flight set |
| FSSM | To be defined by Subcontractor | 3 months after 1st flight set |

The Contractor shall provide an itemized price breakdown for all spares.

The supplier shall ensure sufficient spare stock to be available within 4 weeks in order to replenish any depleted item of the delivered spare set.

## Options

Mandatory Options:

Option 1: Flight Set FM2 (SAT-B)

Option 2: Flight Set FM3 (SAT-C)

Option 3: Thermal Hardware Integration Activities as per chapter 4.2 and chapter 6.

## Customer Undertakings

| No. | Item | Description | Delivery Date |
| --- | --- | --- | --- |
| 1 | Input : CAD model |  | Kick-Off |

Table 4-3: Customer Undertakings

## Delivery Address

The delivery address shall be:

Airbus Defence & Space GmbH, Graf von Soden Straße / Werk 2, 88090 Immenstaad/Germany

# Milestones, Meetings and Review Dates

The supplier shall plan for reviews as requested in the GSoW [AD 2], section 4 and in the documents made applicable.

The supplier is encouraged to propose an efficient and reasonable combination of these reviews, if a commercial or schedule benefit exists.

In view of higher level reviews and milestones to which the supplier input is required, the following schedule boundaries shall apply:

| Equipment Milestone | Date |
| --- | --- |
| Kick-Off | to be proposed by supplier (latest possible kick off to meet required DRB dates) but not before 01.01.2029 |
| EQSR | to be proposed by supplier |
| MPCB/PCB/ERCB | to be proposed by supplier |
| Design Freeze | 6 months before CDR |
| CDR | to be proposed by supplier |
| 1st Flight Set MRR | to be proposed by supplier |
| Test Set MRR | to be proposed by supplier |
| MLI SAT-A DRB | Before 09.2030 |
| Test MLI DRB | TBD |
| Optional 2nd Flight Set DRB | Before 09.2031 |
| Optional 3rd Flight Set DRB | Before 09.2032 (TBC) |
| MIP/KIPs per model | to be proposed by supplier |

Table 5-1: S2NG Meetings and Review Dates

# Specific Requirements and Post Delivery Requirements

## Integration

The Supplier shall make (together with the customer) the integration of the attachment parts and the thermal hardware on the satellite at the contractor’s premises:

- Stand-off gluing

- MLI integration

- Grounding connections

- FSSM bonding (radiators)

## Specific Support and Post Delivery Requirements Mission S2NG.

The Supplier shall prepare to retrofit on the THW-SAT-B/C to any anomaly or findings occurred during the THW-SAT-A built sequence.

The supplier shall provide following post-delivery test support for THW-SAT-A, THW-SAT-B and THW-SAT-C.

- Perform refurbishment of all thermal hardware after mechanical testing (if necessary)

- Trimming of THW-SAT-A MLI on Radiator surfaces after SAT-A test campaign

- Trimming of THW-SAT-B/C MLI on Radiator surfaces based on SAT-A flight experience (if applicable).

## Specific Support to Phase E1

N/A

## Lifetime, Long Storage and Maintenance

See GSOW and Specification

## Life Cycle Assessment (LCA)

At a later stage the Contractor shall provide data wrt the environmental impact of the equipment to support the System level LCA. It shall be directly the LCA analysis of the equipment or it shall be data and information collection from the supply chain of the equipment as well as from Contractor’s company know-how (e.g. including energy consumption, water consumption, depletion of mineral and fossil resources…)

To provide input data for the Life Cycle Inventory relevant to the Product(s) under Contractor’s responsibility, aimed at collecting basic information to generate a dataset characterizing the environmental impact of the product(s), to be subsequently exploited by the Customer in the System Level Life Cycle Assessment (LCA) Model.

The basic information data collection shall be performed by the Contractor, whereas the dataset generation will be performed by the Customer.

Data provided in the frame of previous missions shall be re-used if applicable

# Documentation

The list of documents as per [GSOW §9] amended as follow:

Legend:

Classifications

A	to be approved

R	to be reviewed

I	for information only

Formal Submittals:

KO	Kick-off

EQSR	Equipment Qualification Status Review

CDR	Critical Design Review

MRR	Manufacturing Readiness Review

QR	Qualification Review

DRB	Delivery Review Board (applicable for all deliveries: EM, EQM, all FMs)

a/r 	as required

## Documentation for unit falling in Category C or D

Administration, Management and Project Control

| DLR Ref. | Title | Proposal | KO | Design Freeze | CDR | QR | MRR | DRB | Submittal | Classification | Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PM-01 | Project Management Plan |  |  |  |  |  |  |  |  | A | As per Annex A of ECSS-M-ST-10C |
| PM-02 | Progress Report |  |  |  |  |  |  |  | a/r | R | content: see 4.1.1 of this SOW |
| PM-03 | Schedule Reporting (including Master Schedule) | x |  |  |  |  | x |  | a/r | R | after KO as part of Progress report, as per Annex C of ECSS-M-ST-60C and Annex B of ECSS-M-ST-60C |
| PM-04 | Review Data Package |  |  | x | x | x | x | x |  | R | "A" for content of Data Package |
| PM-05 | Change Notice/Change Request |  |  |  |  |  |  |  | a/r | A | As per Annex G/H of ECSS-M-ST-40C |
| PM-06 | Request for Deviation Request for Waiver |  |  | x | x | x | x | x x | a/r | A | For any NC/PC against applicable documents As per Annex I of ECSS-M-ST-40C |
| PM-07 | Project Directory |  |  |  |  |  |  |  | a/r | I | list of project members, roles, coordinates |
| PM-08 | List of Acronyms and Abbreviations |  |  |  |  |  |  |  | a/r | I | if not covered in specific documentation |
| PM-09 | Not applicable |  |  |  |  |  |  |  |  |  |  |
| PM-10 | Configuration Item Data List |  |  |  |  | x | x | x | a/r | R | ECSS-M-ST-40C, Annex C |
| PM-11 | Export License |  |  |  |  |  |  | x |  | I | See also Annex A |
| PM-12 | REACh Declaration Form |  |  |  | x |  |  | x |  | R | see chapter 8.5.2 |
| PM-13 | REACh Safe Use Instruction |  |  |  |  |  |  | x |  | R | see chapter 8.5.2 |
| PM-14 | Inventory Record |  |  |  |  |  |  | x |  | R | As per Annex I of ECSS-M-ST-60C |
| PM-15 | Export Control List | x |  | x | x |  |  | x | a/r | R | See also Annex A |
| PM-16 | Configuration Management Plan |  |  |  |  |  |  |  |  | A | According to ECSS-M-ST-40C, Annex A. or included in PM-01 |
| PM-17 | Risk Management Plan |  |  |  |  |  |  |  |  | A | Selfstanding document or included in PM-01 |
| PM-18 | Work Breakdown Structure |  |  |  |  |  |  |  |  | A | As per Annex C of ECSS-M-ST-10C |
| PM-19 | Work Package Description |  |  |  |  |  |  |  |  | A | As per Annex C of ECSS-M-ST-10C |
| PM-20 | Milestone Payment Plan (MPP) | x |  |  |  |  |  |  |  | A | As per Annex H of ECSS-M-ST-60C |
| PM-21 | Compliance Matrix to SOW | x |  |  |  |  |  |  |  | A |  |
| PM-22 | RFD/RFW Status List |  |  | x | x | x | x | x |  | I | As per Annex I of ECSS-M-ST-40C |

Technical Documents

| DRL Ref. | Title | Proposal | KO | Design freeze | CDR | QR | MRR | DRB | Submittal | Classification | Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TD-01 | Design Description & Performance Justification | x |  | x | x | x |  | x |  | R | - Design Description Design Performance and Function as per Annex G of ECSS-E-ST-10C |
| TD-02 | Interface Control Document(s) | x |  | x | x | x | x | x | a/r | A | - MICD - TICD - Budgets As per Annex E of ECSS-E-ST-10C |
| TD-03 | Design, Development & Verification Plan | x |  | x | x |  |  |  |  | A | As per Annex A of ECSS-E-ST-10-02C and Annex F of ECSS-Q-ST-60-02C |
| TD-04 | Lower Level Requirements Specifications |  |  | x | x |  |  |  |  | R | As per Annex A of ECSS-E-ST-10-06C |
| TD-05 | Verification Control Document |  |  | x | x | x |  | x |  | R | Reference between requirements given in the specification and their verification - in line with ECSS-E-ST10-02C Annex B. Including compliance matrix |
| TD-06 | Test Plan (including test matrix) |  |  | x | x | x |  |  |  | A | As per Annex A of ECSS-E-ST-10-03C |
| TD-10 | Test Procedures |  |  |  | x |  |  |  | a/r | R | Latest 2 weeks before tests As per Annex C of ECSS-E-ST-10-03C |
| TD-11 | Test Reports |  |  |  |  | x |  | x | a/r | R | As per Annex C of ECSS-E-ST-10-02C |
| TD-12 | Qualification Report |  |  |  |  | x |  |  |  | R | see 3.5.2.8 of this SoW and as per Annex C of ECSS-Q-ST-70-60C |
| TD-13 | Handling/Packing/Transportation/Storage Manual |  |  | x | x | x |  | x |  | R | Or included in TD-14 |
| TD-14 | User Manual |  |  | x | x | x |  | x |  | R | As per annex P of ECSS-E-ST-10C |
| TD-58 | Compliance Matrix to the Technical Specification | x |  | x | x | x |  |  |  | A |  |
| TD-59 | CIDL |  |  | x | x | x |  | x |  | A | As per ECSS-M-ST-40C ABCL for unit specific reviews |

Product Assurance Documents

| DRL Ref. | Title | Proposal | KO | Design freeze | CDR | QR | MRR | DRB | Submittal | Classification | Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PA-01 | PA-Plan | x |  | x | x |  |  |  |  | A |  |
| PA-02 | Long Lead Items List |  |  |  |  |  |  |  |  | R |  |
| PA-03 | Qualification Status List | x |  | x | x | x |  |  |  | R | As per Annex B of ECSS-Q-ST-10C |
| PA-04 | MIP Reports |  |  |  |  |  |  | x | a/r | R | As per Annex E of ECSS-E-ST-10-02C and Annex D of ECSS-Q-ST-5-50C |
| PA-05 | NCR´s |  |  |  |  |  |  |  | a/r | A/I | As per Annex A of ECSS-Q-ST-10-09C |
| PA-06 | Audit Plan & Reports |  |  |  |  |  |  |  | a/r | I | if applicable |
| PA-07 | Critical Items List | x |  | x | x |  |  |  |  | R | As per Annex A of ECSS-Q-ST-10-04C and as defined in PARS |
| PA-08 | Reliability Analysis |  |  | x | x |  |  | x |  | R | As per Annex E of ECSS-Q-ST-30C |
| PA-09 | Failure Mode Effects and Criticality Analyses (FMECA) |  |  | x | x | x |  |  | a/r | R | As per Annex A of ECSS-Q-ST-30-02C |
| PA-10 | Radiation Analysis |  |  | x | x |  |  | x |  | R | As per Annex B of ECSS-Q-ST-60-15C |
| PA-11 | Worst Case Analysis |  |  | x | x |  |  | x |  | R | As per Annex J of ECSS-Q-ST-30C |
| PA-12 | Parts Stress Analysis |  |  | x | x |  |  | x |  | R | As per ECSS-Q-ST-30-11C (includes de-rating analysis) |
| PA-13 | Safety Analysis |  |  | x | x |  |  | x |  | R | as input to System Safety Analysis |
| PA-14 | Declared Materials List (DML) | x |  | x | x | x |  | x |  | A | As per Annex A of ECSS-Q-ST-70C |
| PA-15 | Declared Mechanical Parts List (DMPL) | x |  | x | x | x |  | x |  | A | As per Annex B of ECSS-Q-ST-70C (can be combined with DML) |
| PA-16 | Declared Processes List | x |  | x | x | x |  | x |  | A | As per Annex C of ECSS-Q-ST-70C |
| PA-17 | Declared Components List, EEE-Parts List (DCL) | x |  | x | x | x | x | x |  | A | As per Annex B of ECSS-Q-ST-60C |
| PA-18 | Parts Approval Document (PAD) |  |  | x | x |  | x |  | a/r | A | As per Annex D of ECSS-Q-ST-60-13C |
| PA-19 | Request for Approval (RFA) |  |  |  |  |  | x |  | a/r | A | As per Annex D of ECSS-Q-ST-70C |
| PA-20 | End Item Data Package (EIDP) |  |  |  |  |  |  | x |  | A | see Annex B of this document |
| PA-21 | Compliance Matrix to PA requirements | x |  | x | x |  |  |  |  | A |  |
| PA-22 | MIP/KIP List |  |  |  |  |  |  |  |  | R |  |
| PA-23 | Cleanliness and Contamination Control Plan (CCCP) |  |  |  |  |  |  |  | a/r | A | As per annex A of ECSS‐Q‐ST‐70‐01C |

End of Document